## 1. Organize
OT Patching and Vulnerability Management Playbook - Organize
The purpose of the 'ORGANIZE' section is to help the BU collect the relevant information about the vulnerability, as well as identify stakeholders across the organization that would be responsible, accountable, consulted, or informed (RACI) about remediation activities. The stakeholders include both internal and external customers, services providers, and vendors that may be involved in the operation of the system. This section also includes identification of assets impacted or effected by the vulnerability as well as other analysis of the relative risk posed by the vulnerability. The output of this section should be used in the 2. PREPARE tab to create a strategy and roadmap for remediation.
Business Unit
Department
I - Organize
Information for this section is available from the Armis or reported device vulnerabilities. The vendors identified in the report may not be exactly the same as those in the advisory since some devices may be OEM devices. If this is the case, list the vendor and note any differences or relationships between vendors as necessary.
Advisory Number |  |  | Device Category |  | Vendor | Device Model | Site Locations | Notes
☐
☐
☐
☐
☐
☐
☐
☐
1.0 Respond The purpose of this section is to respond, acknowledge, and accept the remediation request into your BUs project/action/intake system.
Activity |  |  |  | Description |  |  | Governance
☐ | 1.1 Enter vulnerability into your BU's intake process |  |  | This action acknowledges the vulnerability to the organization, and the fact that a decision must be made on how to deal with it. The intake location where projects and actions are initiated for your organization. This includes Service Now or any other ticketing system where you acknowledge requests for service and action for your system. This may also be a project intake system where you schedule activities for various projects and initiatives.
☐ | 1.2 Determine System Ownership and Responsibility |  |  | Review the Armis search spreadsheet to determine the system owners and custodians involved in the decision making and administration of the systems. Make this determination based on system categories and it's business purpose.
☐ | 1.3- Appoint POC/Program Manager |  |  | Appoint a single point of contact or project manager within your organization that will lead remediation efforts and receive communications for all matters related to remediation efforts. This is the person who is the single point of contact for communication on the issue, and will lead the planning, tracking, and execution efforts of the vulnerability remediation. Ideally, this person already has knowledge or the system, or has led other implementation efforts around this system.
☐ | 1.4 - |  |  | Add more tasks as necessary below for response and acknowledgements specific to your BU.
☐
☐
2.0 Analyze
Activity |  |  |  | Description |  |  | Notes
☐ | 2.1 Review report to determine which assets from your organization are Impacted or identified as affected by the CVE. |  |  | Used to determine scope and foot print of vulnerabilities with your group. Identify groups and category of devices - ie IP Cameras, PLCs, Handhelds, etc. Also determine which CVE applies to which group. The Armis device list will tell which CVEs apply to each type to avoid confusion about which vulnerabilities apply.
☐ | 2.2 Determine Sites Impacted by the CVE or advisory |  |  | Not all sites may have assets impacted by this vulnerability. The reason may be that each site uses different models of devices and different operating software. Identify these sites as well as those which are the most critical sites from a business perspective especially when a severe criticality that has been exploited exists.
☐ | 2.3 Determine Business Processes Impacted |  |  | OT devices support a business process - ie materials handling, inventory, logistics, CRM, Warehouse Management, etc. Knowing this information will assist in identifying how that process will continue during remediation efforts.
☐ | 2.4 Determine Customers Impacted (internal/external) |  |  | Identify which customers are impacted due to interruption of a business process - internal and external. They may need to be notified of system unavailability or delays if remediation affects their activities.
☐ | 2.5 Determine internal/external stakeholders |  |  | Identify anyone else that could participate or be impacted by remediation - ie IT support, IT infrastructure, IT Support, Vendors, 3rd party service providers, ISPs, etc. You may need these individuals to assist in planning activities.
☐ | 2.6 Determine Data Stores impacted if applicable |  |  | Identify where data is stored for the system and business processes (databases, storage volumes, backups and snapshots. Determine alternate sites and currency of the data and recovery point objectives should they need to be restored if an incident occurs during remediation.
☐ | 2.7 Determine additional dependencies and constraints including system, business, and resources. |  |  | Identify other systems, activities, or processes that create dependencies for the upgrade - this includes infrastructure capacity, support resources, critical workloads (on premise or cloud) that must be considered in order to execute remediation activities.
☐ | 2.8 Determine Relative Risk based on impact, severity, and threat landscape (Low, Med, High) |  |  | Not every CVE poses the same level of risk for every system and organization - even if it is critical. Existing controls may lower the actual risk presented by the vulnerability, or if nothing is impacted (affected) by the vulnerability, no risk may exist. Use your preferred risk assessment method or the Risk Assessment Tab to do a simple assessment of relative risk of the vulnerability. Use the relative risk score to assist in prioritization of CVE remediation.
☐
☐
☐
3.0 Communicate
Activity |  |  |  | Description
☐ | Contact asset vendors for advisory guidance |  |  | A discussion with the vendor may save lots of time in developing and executing a strategy. They can also pass advice and best practices as how to deal wth this type of issue. They may also help you assess risk and develop a remediation strategy. Make this the 1st communication you make after becoming aware of the vulnerability. The vendor's website may have preliminary information on the vulnerability, however the support engineers from the company are a valuable resource when planning remediation efforts.
☐ | Contact 3rd party support and service providers as necessary |  |  | This includes any managed services organizations or cloud-providers responsible for the upkeep and administration of the system. Use their ticketing or in-take system to gain recognition of the issue for planning and support purposes.
☐ | Notify BISO and ISRM contacts of intent to address vulerability |  |  | ISRM (Information Security and Risk Management) compiles and reports metrics to senior management on risk management activities such as vulnerability management. ISRM may have notified you of the vulernability via a JIRA ticket or even email. Use whatever method agreed upon to let them know that the issue is under consideration in order to begin the compilation of metrics.
☐ | Identify and Assemble stakeholders as needed in order to plan executing of vulnerability remediation. |  |  | Stakholders in the VM process include those listed below
☐ | *IT-related stakeholders - |  |  | Network Support, Infrastructure (Virtual Services, Data Center, Physical Servers, etc), Network Security (IAM, FW, or other Security Tools) whether internal or third party support.
☐ | *System Owners, Custodians, Developers |  |  | Technology Asset Owners responsible for the operation, maintenance, or development of applications and tools relevant to the devices in question.
☐ | *Business Unit and Site Leads |  |  | Business representatives including product
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐

## 2. Prepare
OT Patching and Vulnerability Management Playbook - Prepare
Objective: The objective of the PREPARE section is to assist stakeholders in developing a strategy to remediate vulnerabilities, and then identify and plan for categories of resources required for successful remediation. This is input to the EXECUTE section of the spreadsheet.
Business Unit
|  | Department |  |  |  |  | Date
ADDITIONAL INFO
II - Prepare
4.0 Strategize
| Activity |  |  |  | Description | Output and or Links
| ☐ | Determine the level of risk based on the severity
| ☐ | Identify and Review Applicable security policies and procedures. The McKesson Enterprise Vulnerability Management can be found below. It describes the roles and responsibilties of staff to identify, assess, and remediate security vulnerabilities as well as any requirements for exceptions. |  |  | https://mckessoncorp.sharepoint.com/sites/Policies/SitePages/Threat-and-Vulnerability-Management-Policy.aspx
| ☐ | Determine Approach Based on Analysis:
| ☐ | Patch Vulnerability - Single Patch |  |  | Install additional libraries, software, and firmware necessary to address vulnerability
| ☐ | Patch Vulnerability - Aggregated or Combined Patching |  |  | Install additional libraries, software, and firmware necessary to address multiple vulnerabilities at one time from previous notices. Note: Specify CVE ID's or other notices to aggregate.
| ☐ | Upgrade |  |  | Install major release or version number that addresses vulnerability and provides additional system features desired.
| ☐ | Mitigate with other security controls- |  |  | Monitor, remove, or configure other system features. Install or leverage infrastructure tools like firewalls or segmentation that would lower the risk of the vulnerability without installing new software on the system.
| ☐ | Accept Risk without direct mitigation |  |  | Request exception (Most likely requires executive approval and contingency plans
| ☐ | Define technical, business, and system requirements based on strategy. |  |  | Each strategy requirements.
| ☐ | Prioritize remediation efforts based on risk and business impact |  |  | Prioritize remediation based on business impact and risk since most BUs don't have unlimited resources. Although the strategy shows how you will approach remediation, prioritization shows where and when you execute based on business priorities and risk.
☐
☐
☐
☐
5.0 Govern
| Activity |  |  |  | Description | Output and or Links
| ☐ | Determine Risk Exception process if needed. |  |  | The BU may determine that remediation cannot occur due to various factors. Reach out to the BISO of your organization if needed to determine exception criteria and processes.
| ☐ | Determine executive approvals needed based on strategy. |  |  | Most decisions that impact the availability of the system may require executive approval. Review your organization's policies and procedures to determine which actions require executive approval, and apply for it as necessary to facilitate remediation.
| ☐ | Record risk within applicable risk register
| ☐ | Determine Configuration Control Board (CCB) approvals for system changes.
| ☐ | Identify and determine contractual obligations or restraints for patching and remediation activities.
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
6.0 - Align
| Activity |  |  |  | Description | Output and or Links
| ☐ | Identify other system and business related activity present at this time. Describe how it impacts vulnerability remediation efforts including upgrades, maintenance, and replacements
| ☐ | Identify changes in business processes or value streams that may occur simultaneously with remediation activities
| ☐ | Identify the implementation of other security controls, policies, or configurations that may occur simultaneously with vulnerability remediation activities. (ie segmentation, FW policy changes, threat protection etc.
| ☐ | Identify any architectural changes relevant to vulnerability remediation.
| ☐ | Identify program increments (Pis), EPICs or stories to add remediation activities. Decide which Pis to inject activities based on resources and other scheduled features.
7.0 Plan Use this section to plan details needed to execute the vulnerability remediation or mitigation efforts.
CATEGORY
|  | Resources |  | Responsibilities |  | Description and Notes
| ☐ | Network Administration and Engineering |  | Plan, execute, and monitor network changes and activity during remediation. Identify what support should exist if errors or issues occur during remediation.
| ☐ | Security Administration and Engineering |  | Plan, execute, and monitor network security changes and activity during remediation. Identify what support should exist if errors or issues occur during remediation.
| ☐ | System Administration |  | Plan, execute, and monitor network system changes and activity during remediation. Identify what support should exist if errors or issues occur during remediation.
| ☐ | Site Operations Leads |  | Direct business failover operations and perform testing and verificaion of return to normal business operations.
| ☐ | Site Technical Support |  | Hands on support for any site specific network or systems issues.
| ☐ | 3rd Party IT support |  | Provide Tier 1-3 network and systems support should an incident arise during patching activities. |  | Include any individuals assigned to your organization to support the system in question.
| ☐ | Vendors |  | Consultation and support during patch activities.
☐
☐
☐
☐
☐
☐
| ☐ | Schedule Type |  | Potential Dates | Dependencies | Notes
| ☐ | Testing
| ☐ | Approvals
| ☐ | Change Management
| ☐ | Implementation Management
| ☐ | Configuration Control Board
| ☐ | Access Control - FW rule modifications
| ☐ | Execution Dates
☐
☐
| ☐ | Documentation |  |  | Description
| ☐ | Vendor Upgrade and Patching procedures
| ☐ | Configuration Management Plans
| ☐ | Change Management policies and procedures |  |  | Used to identify the process controlling changes within the system and organization.
| ☐ | System configuration and support playbooks |  |  | Used to identify how sites will failover key business processes if necessary during remediation activities. Also used to identify decision makers to activate continuity plans if an incident occures.
| ☐ | Incident Management Plans
| ☐ | Business Continuity Plans
| ☐ | Disaster Recovery Plans |  |  | Used to identify recovery, backup, and alternate site procedures.
| ☐ | Security policies and procedures
☐
☐
☐
☐
☐
| ☐ | Testing
| ☐ | Identify testing resources and systems.
| ☐ | Identify changes to testing environment necessary to evaluate patching procedures.
| ☐ | Identify additional tools and applications used to test patch or remediation activities.
☐
☐
☐
☐
☐
☐
| ☐ | Business Continuity
| ☐ | Identify business and process failovers during upgrades or patching.
| ☐ | Identify alternate sites for business activities during patching and failovers.
☐
☐
☐
| ☐ | Disaster Recovery
| ☐ | Identify backup systems, alternate sites, or regions used for disaster recover.
| ☐ | Identify data and configuration backups required for recovery if necessary.
| ☐ | Identify system failover procedures for use during patching and upgrades.
| ☐ | Identify rollback procedures for both systems and data.
☐
☐
☐
☐
☐
| ☐ | Configuration Management
| ☐ | Review and determine method of naming and controlling configuration items for the upgrade. |  |  |  | If this is a vendor controlled/operated system or service, they most likely will have this information. If not, this will require greenfield planning.
| ☐ | Determine changes that do not require configuration control or change management control.
| ☐ | Identify impacted configuration items (CI)
| ☐ | Identify configurations that may impact the security of the system |  |  |  | This includes changes in access, authentication, encryption, or any security capability included in the system.
| ☐ | Identify system component inventory
| ☐ | Identify impacted configuration items (CI) |  |  |  | Servers, workstations, HDMI, OS, firmware, communications devices, or application suite tracked.
| ☐ | Identify a baseline configuration for the system |  |  |  | Set of specifications that has been reviewed and agreed upon for operating the system.
| ☐ | Identify Configuration monitoring processes required during change
| ☐ | Perform a security impact analysis to determine whether upgrade, patch, or reconfiguration changes security functionality or existing controls |  |  |  | This prevents accidental errors that could impact the surity of a system - ie access, authorizations, encryption, privacy, etc.
| ☐ | Make Change Requests for changes of impacted CIs.
| ☐ | Security Management
| ☐ | Identify changes to access control/FW devices necessary
| ☐ | Review amd determine whether additional authorizations and privileges are necessary for staff to execute changes.
| ☐ | Apply for additional privileged access if necessary prior to the upgrade.
| ☐ | Review whether remote access is necessary for 3rd parties to participate in patch and upgrade activities.
| ☐ | Apply for additional remote access if necessary prior to the upgrade.
☐
☐
☐
☐
| ☐ | Network Management
| ☐ | Identify network (vlan, IP addressing, routing, and switching changes that may be necessary for remediation or mitigation of the risk or vulnerability.
| ☐ | Identify network capacity or performance issues that may impact an upgrade or patch activities.
| ☐ | Identify other network related activity that may impact vulnerability remediation plans.
☐
| ☐ | Incident Management
| ☐ | Identify procedures to request support during an incident
| ☐ | Identify indivduals who fill the incidenet manager role if necessary.
| ☐ | Identify groups or individuals that may serve as the incident resolution team if necessary.
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| ☐ | Closure
☐
☐
☐
☐
☐
☐
☐
☐
☐
III - Execute
IV - Evolve

## 3. Execute
OT Patching and Vulnerability Management Playbook - Execute
Objective: Use the 'Execute' section of the playbook as a step-by-step guide to conducting the remediation. Include in the execution all the areas planned for in the 'Prepare' section of the playbook. Feel free to add any other areas identified that could be relevant to your operation.
Business Unit
|  | Department | [7 empty] | Date
ADDITIONAL INFO
I - Organize
|  |  | 2.0 Analyze |  |  |  | 3.0 Communicate |  |  |  | Would like to provide hyperlinks in each one of these activities to where this should be done or another tracking tool within this spreadsheet or smart sheet.
|  |  | ☐ | Determine Impacted Assets or Inventory (Armis or other TVM tool) |  |  | ☐ | Contact asset vendors for advisory guidance |  |  | Note: do I need to provide a checklist for OT team?
|  |  | ☐ | Determine Sites Impacted |  |  | ☐ | Include 3rd party support and service providers as necessary
|  |  | ☐ | Determine Business Processes Impacted |  |  | ☐ | Contact asset vendors for advisory guidance |  |  | We need a configuration control board (CCB)
|  |  | ☐ | Determine Customers Impacted (internal/external) |  |  | ☐ | Notify BISO and ISRM contacts of intent to address vulerability
|  |  | ☐ | Determine Data Stores impacted if applicable |  |  | ☐ | Identify and Assemble stakeholders as needed in order to plan executing of vulnerability remediation.
|  |  | ☐ | Determine internal/external stakeholders |  |  | ☐ | IT-related stakeholders - Network, Infrastructure, ISRM
|  |  | ☐ | Determine additional dependencies and constraints including system, business, and resources. |  |  | ☐ | System Owners, Custodians, Developers
|  |  | ☐ | Determine Relative Risk based on impact, severity, and threat landscape (Low, Med, High) |  |  | ☐ | Business Unit and Site Leads
1.0 Respond
| Activity |  |  |  |  | Description |  |  | Output
| ☐ | 1.1.1 Enter vulnerability into intake process
| ☐ | 1.1.2 Determine System Ownership and Responsibility
| ☐ | 1.1.3 - Appoint POC/Program Manager
☐
☐
☐
☐
☐
☐
☐
☐
2.0 Analyze
| Activity |  |  |  |  | Description |  |  | Output
| ☐ | Determine Impacted Assets or Inventory (Armis or other TVM tool)
| ☐ | Determine Sites Impacted
| ☐ | Determine Business Processes Impacted
| ☐ | Determine Customers Impacted (internal/external)
| ☐ | Determine Data Stores impacted if applicable
| ☐ | Determine internal/external stakeholders
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
3.0 Communicate
| Activity |  |  |  |  | Description |  |  | Output
☐
☐
☐
☐
☐
III-Execute
| Activity |  |  |  |  | Description |  |  | Output
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| Activity |  |  |  |  | Description |  |  | Output
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| Activity |  |  |  |  | Description |  |  | Output
☐
☐
☐
☐
☐
Use this section to execute the vulnerability remediation or mitigation efforts.
CATEGORY
|  | Resources |  |  | Responsibilities |  |  |  | Description and Notes
| ☐ | Network Administration and Engineering |  |  | Plan, execute, and monitor network changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | Security Administration and Engineering |  |  | Plan, execute, and monitor security changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | System Administration |  |  | Plan, execute, and monitor system changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | Site Operations Leads |  |  | Direct business failover operations and perform testing and verificaion of return to normal business operations.
| ☐ | Site Technical Support |  |  | Hands on support for any site specific network or systems issues.
| ☐ | 3rd Party IT support |  |  | Provide Tier 1-3 network and systems support should an incident arise during patching activities. |  |  |  | Include any individuals assigned to your organization to support the system in question.
| ☐ | Vendors |  |  | Consultation and support during patch activities.
☐
☐
☐
☐
☐
☐
| ☐ | Schedule Type |  |  | Potential Dates | Dependencies |  |  | Description and Notes
| ☐ | Testing
| ☐ | Approvals
| ☐ | Change Management
| ☐ | Implementation Management
| ☐ | Configuration Control Board
| ☐ | Access Control - FW rule modifications
| ☐ | Execution Dates
☐
☐
| ☐ | Documentation
| ☐ | Vendor Upgrade and Patching procedures
| ☐ | Configuration Management Plans
| ☐ | Change Management policies and procedures | [6 empty] | Used to identify the process controlling changes within the system and organization.
| ☐ | System configuration and support playbooks
| ☐ | Incident Management Plans
| ☐ | Business Continuity Plans | [6 empty] | Used to identify how sites will failover key business processes if necessary during remediation activities. Also used to identify decision makers to activate continuity plans if an incident occures.
| ☐ | Disaster Recovery Plans | [6 empty] | Used to identify recovery, backup, and alternate site procedures.
| ☐ | Security policies and procedures
☐
☐
☐
☐
☐
| ☐ | Testing
| ☐ | Identify testing resources and systems.
| ☐ | Identify changes to testing environment necessary to evaluate patching procedures.
| ☐ | Identify additional tools and applications used to test patch or remediation activities.
☐
☐
☐
☐
☐
☐
| ☐ | Business Continuity
| ☐ | Identify business and process failovers during upgrades or patching.
| ☐ | Identify alternate sites for business activities during patching and failovers.
☐
☐
☐
| ☐ | Disaster Recovery
| ☐ | Identify backup systems, alternate sites, or regions used for disaster recover.
| ☐ | Identify data and configuration backups required for recovery if necessary.
| ☐ | Identify system failover procedures for use during patching and upgrades.
| ☐ | Identify rollback procedures for both systems and data.
☐
☐
☐
☐
☐
| ☐ | Configuration Management
| ☐ | Review and determine method of naming and controlling configuration items for the upgrade. | [6 empty] | If this is a vendor controlled/operated system or service, they most likely will have this information. If not, this will require greenfield planning.
| ☐ | Determine changes that do not require configuration control or change management control.
| ☐ | Identify impacted configuration items (CI)
| ☐ | Identify configurations that may impact the security of the system | [6 empty] | This includes changes in access, authentication, encryption, or any security capability included in the system.
| ☐ | Identify system component inventory
| ☐ | Identify impacted configuration items (CI) | [6 empty] | Servers, workstations, HDMI, OS, firmware, communications devices, or application suite tracked.
| ☐ | Identify a baseline configuration for the system | [6 empty] | Set of specifications that has been reviewed and agreed upon for operating the system.
| ☐ | Identify Configuration monitoring processes required during change
| ☐ | Perform a security impact analysis to determine whether upgrade, patch, or reconfiguration changes security functionality or existing controls | [6 empty] | This prevents accidental errors that could impact the surity of a system - ie access, authorizations, encryption, privacy, etc.
| ☐ | Make Change Requests for changes of impacted CIs.
| ☐ | Security Management
| ☐ | Identify changes to access control/FW devices necessary
| ☐ | Review amd determine whether additional authorizations and privileges are necessary for staff to execute changes.
| ☐ | Apply for additional privileged access if necessary prior to the upgrade.
| ☐ | Review whether remote access is necessary for 3rd parties to participate in patch and upgrade activities.
| ☐ | Apply for additional remote access if necessary prior to the upgrade.
☐
☐
☐
☐
| ☐ | Network Management
| ☐ | Identify network (vlan, IP addressing, routing, and switching changes that may be necessary for remediation or mitigation of the risk or vulnerability.
| ☐ | Identify network capacity or performance issues that may impact an upgrade or patch activities.
| ☐ | Identify other network related activity that may impact vulnerability remediation plans.
☐
| ☐ | Incident Management
| ☐ | Identify procedures to request support during an incident
| ☐ | Identify indivduals who fill the incidenet manager role if necessary.
| ☐ | Identify groups or individuals that may serve as the incident resolution team if necessary.
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| ☐ | Closure
☐
☐
☐
☐
☐
☐
☐
☐
☐
III - Execute
IV - Evolve

## 4. Evolve
OT Patching and Vulnerability Management Playbook - Evolve
Objective: Use this section to identify lessons learned from the execution of the vulnerability remediation. Continuous improvement ensures that the next remediation plan will correct defits or failures that occurred during a previous execution. Schedule a 'Lessons Learned' meeting as soon as possible after execution to ensure that all actors and stakeholders do not forget incidents or issues that occurred during remediation.
Business Unit
|  | Department | [9 empty] | Date
ADDITIONAL INFO
IV - Evolve
CATEGORY
|  | Resources |  |  |  | Responsibilities |  |  |  |  | Description and Notes
| ☐ | Network Administration and Engineering |  |  |  | Plan, execute, and monitor network changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | Security Administration and Engineering |  |  |  | Plan, execute, and monitor security changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | System Administration |  |  |  | Plan, execute, and monitor system changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | Site Operations Leads |  |  |  | Direct business failover operations and perform testing and verificaion of return to normal business operations.
| ☐ | Site Technical Support |  |  |  | Hands on support for any site specific network or systems issues.
| ☐ | 3rd Party IT support |  |  |  | Provide Tier 1-3 network and systems support should an incident arise during patching activities. |  |  |  |  | Include any individuals assigned to your organization to support the system in question.
| ☐ | Vendors |  |  |  | Consultation and support during patch activities.
☐
☐
☐
☐
☐
☐
| ☐ | Schedule Type |  |  |  | Potential Dates | Dependencies |  |  |  | Description and Notes
| ☐ | Testing
| ☐ | Approvals
| ☐ | Change Management
| ☐ | Implementation Management
| ☐ | Configuration Control Board
| ☐ | Access Control - FW rule modifications
| ☐ | Execution Dates
☐
☐
| ☐ | Documentation
| ☐ | Vendor Upgrade and Patching procedures
| ☐ | Configuration Management Plans
| ☐ | Change Management policies and procedures | [8 empty] | Used to identify the process controlling changes within the system and organization.
| ☐ | System configuration and support playbooks
| ☐ | Incident Management Plans
| ☐ | Business Continuity Plans | [8 empty] | Used to identify how sites will failover key business processes if necessary during remediation activities. Also used to identify decision makers to activate continuity plans if an incident occures.
| ☐ | Disaster Recovery Plans | [8 empty] | Used to identify recovery, backup, and alternate site procedures.
| ☐ | Security policies and procedures
☐
☐
☐
☐
☐
| ☐ | Testing
| ☐ | Identify testing resources and systems.
| ☐ | Identify changes to testing environment necessary to evaluate patching procedures.
| ☐ | Identify additional tools and applications used to test patch or remediation activities.
☐
☐
☐
☐
☐
☐
| ☐ | Business Continuity
| ☐ | Identify business and process failovers during upgrades or patching.
| ☐ | Identify alternate sites for business activities during patching and failovers.
☐
☐
☐
| ☐ | Disaster Recovery
| ☐ | Identify backup systems, alternate sites, or regions used for disaster recover.
| ☐ | Identify data and configuration backups required for recovery if necessary.
| ☐ | Identify system failover procedures for use during patching and upgrades.
| ☐ | Identify rollback procedures for both systems and data.
☐
☐
☐
☐
☐
| ☐ | Configuration Management
| ☐ | Review and determine method of naming and controlling configuration items for the upgrade. | [8 empty] | If this is a vendor controlled/operated system or service, they most likely will have this information. If not, this will require greenfield planning.
| ☐ | Determine changes that do not require configuration control or change management control.
| ☐ | Identify impacted configuration items (CI)
| ☐ | Identify configurations that may impact the security of the system | [8 empty] | This includes changes in access, authentication, encryption, or any security capability included in the system.
| ☐ | Identify system component inventory
| ☐ | Identify impacted configuration items (CI) | [8 empty] | Servers, workstations, HDMI, OS, firmware, communications devices, or application suite tracked.
| ☐ | Identify a baseline configuration for the system | [8 empty] | Set of specifications that has been reviewed and agreed upon for operating the system.
| ☐ | Identify Configuration monitoring processes required during change
| ☐ | Perform a security impact analysis to determine whether upgrade, patch, or reconfiguration changes security functionality or existing controls | [8 empty] | This prevents accidental errors that could impact the surity of a system - ie access, authorizations, encryption, privacy, etc.
| ☐ | Make Change Requests for changes of impacted CIs.
| ☐ | Security Management
| ☐ | Identify changes to access control/FW devices necessary
| ☐ | Review amd determine whether additional authorizations and privileges are necessary for staff to execute changes.
| ☐ | Apply for additional privileged access if necessary prior to the upgrade.
| ☐ | Review whether remote access is necessary for 3rd parties to participate in patch and upgrade activities.
| ☐ | Apply for additional remote access if necessary prior to the upgrade.
☐
☐
☐
☐
| ☐ | Network Management
| ☐ | Identify network (vlan, IP addressing, routing, and switching changes that may be necessary for remediation or mitigation of the risk or vulnerability.
| ☐ | Identify network capacity or performance issues that may impact an upgrade or patch activities.
| ☐ | Identify other network related activity that may impact vulnerability remediation plans.
☐
| ☐ | Incident Management
| ☐ | Identify procedures to request support during an incident
| ☐ | Identify indivduals who fill the incidenet manager role if necessary.
| ☐ | Identify groups or individuals that may serve as the incident resolution team if necessary.
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| ☐ | Closure
☐
☐
☐
☐
☐
☐
☐
☐
☐
Lessons learned for Each of the following areas:
|  |  |  | 2.0 Analyze |  |  |  |  | 3.0 Communicate |  |  |  |  | Would like to provide hyperlinks in each one of these activities to where this should be done or another tracking tool within this spreadsheet or smart sheet.
|  |  |  | ☐ | Determine Impacted Assets or Inventory (Armis or other TVM tool) |  |  |  | ☐ | Contact asset vendors for advisory guidance |  |  |  | Note: do I need to provide a checklist for OT team?
|  |  |  | ☐ | Determine Sites Impacted |  |  |  | ☐ | Include 3rd party support and service providers as necessary
|  |  |  | ☐ | Determine Business Processes Impacted |  |  |  | ☐ | Contact asset vendors for advisory guidance |  |  |  | We need a configuration control board (CCB)
|  |  |  | ☐ | Determine Customers Impacted (internal/external) |  |  |  | ☐ | Notify BISO and ISRM contacts of intent to address vulerability
|  |  |  | ☐ | Determine Data Stores impacted if applicable |  |  |  | ☐ | Identify and Assemble stakeholders as needed in order to plan executing of vulnerability remediation.
|  |  |  | ☐ | Determine internal/external stakeholders |  |  |  | ☐ | IT-related stakeholders - Network, Infrastructure, ISRM
|  |  |  | ☐ | Determine additional dependencies and constraints including system, business, and resources. |  |  |  | ☐ | System Owners, Custodians, Developers
|  |  |  | ☐ | Determine Relative Risk based on impact, severity, and threat landscape (Low, Med, High) |  |  |  | ☐ | Business Unit and Site Leads
1.0 Respond
| Activity | [5 empty] | Description |  |  |  | Output
| ☐ | 1.1.1 Enter vulnerability into intake process
| ☐ | 1.1.2 Determine System Ownership and Responsibility
| ☐ | 1.1.3 - Appoint POC/Program Manager
☐
☐
☐
☐
☐
☐
☐
☐
2.0 Analyze
| Activity | [5 empty] | Description |  |  |  | Output
| ☐ | Determine Impacted Assets or Inventory (Armis or other TVM tool)
| ☐ | Determine Sites Impacted
| ☐ | Determine Business Processes Impacted
| ☐ | Determine Customers Impacted (internal/external)
| ☐ | Determine Data Stores impacted if applicable
| ☐ | Determine internal/external stakeholders
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
3.0 Communicate
| Activity | [5 empty] | Description |  |  |  | Output
☐
☐
☐
☐
☐
II - Prepare
|  | 4.0 Strategize |  |  |  |  | 5.0 Govern | [5 empty] | 6.0 Align |  | Need to change order - put strategize last after the governance and alignment activities.
|  | ☐ | Determine Approach Based on Analysis: |  |  |  | ☐ | Identify and Review Applicable security policies and procedures. |  |  |  |  | ☐ | Identify other system and business related activity present at this time. Describe how it impacts vulnerability remediation efforts including upgrades, maintenance, and replacements
|  | ☐ | Patch - install additional libraries, software, and firmware necessary to address vulnerability |  |  |  | ☐ | Determine Risk Exception process if needed. |  |  |  |  | ☐ | Identify changes in business processes or value streams that may occur simultaneously with remediation activities
|  | ☐ | Upgrade - Install major release or version number that addresses vulnerability and provides additional system features desired. |  |  |  | ☐ | Determine executive approvals needed based on strategy. |  |  |  |  | ☐ | Identify the implementation of other security controls, policies, or configurations that may occur simultaneously with vulnerability remediation activities. (ie segmentation, FW policy changes, threat protection etc.
|  | ☐ | Mitigate with other security controls- monitor, remove, or configure other system features. Install or leverage infrastructure tools like firewalls or segmentation that would lower the risk of the vulnerability without installing new software on the system. |  |  |  | ☐ | Record risk within applicable risk register |  |  |  |  | ☐ | Identify any architectural changes relevant to vulnerability remediation.
|  | ☐ | Accept Risk without direct mitigation - request exception (Most likely requires executive approval and contingency plans |  |  |  | ☐ | Determine Configuration Control Board (CCB) approvals for system changes. |  |  |  |  | ☐
|  | ☐ | Define technical, business, and system requirements based on strategy. |  |  |  | ☐ | Identify and determine contractual obligations or restraints for patching and remediation activities. |  |  |  |  | ☐
|  | ☐ |  |  |  |  | ☐ | [5 empty] | ☐
| Activity | [5 empty] | Description |  |  |  | Output
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| Activity | [5 empty] | Description |  |  |  | Output
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| Activity | [5 empty] | Description |  |  |  | Output
☐
☐
☐
☐
☐

## Template 2
OT Patching and Vulnerability Management Playbook
Objective:
Business Unit
|  | Department | [8 empty] | Date
ADDITIONAL INFO
I - Organize
[5 empty] | 3.0 Communicate |  |  |  | Would like to provide hyperlinks in each one of these activities to where this should be done or another tracking tool within this spreadsheet or smart sheet.
[5 empty] | ☐ |  |  |  | Note: do I need to provide a checklist for OT team?
☐
[5 empty] | ☐ |  |  |  | We need a configuration control board (CCB)
☐
☐
☐
☐
☐
1.0 Respond
| Activity | [5 empty] | Description |  |  | Output
| ☐ | 1.1.1 Enter vulnerability into intake process
| ☐ | 1.1.2 Determine System Ownership and Responsibility
| ☐ | 1.1.3 - Appoint POC/Program Manager
☐
☐
☐
☐
☐
☐
☐
☐
2.0 Analyze
| Activity | [5 empty] | Description |  |  | Output
| ☐ | Determine Impacted Assets or Inventory (Armis or other TVM tool)
| ☐ | Determine Sites Impacted
| ☐ | Determine Business Processes Impacted
| ☐ | Determine Customers Impacted (internal/external)
| ☐ | Determine Data Stores impacted if applicable
| ☐ | Determine internal/external stakeholders
| ☐ | Determine additional dependencies and constraints including system, business, and resources.
| ☐ | Determine Relative Risk based on impact, severity, and threat landscape (Low, Med, High)
☐
☐
3.0 Communicate
| Activity | [5 empty] | Description |  |  | Output
| ☐ | Contact asset vendors for advisory guidance
| ☐ | Include 3rd party support and service providers as necessary
| ☐ | Contact asset vendors for advisory guidance
| ☐ | Notify BISO and ISRM contacts of intent to address vulerability
| ☐ | Identify and Assemble stakeholders as needed in order to plan executing of vulnerability remediation.
| ☐ | IT-related stakeholders - Network, Infrastructure, ISRM
| ☐ | System Owners, Custodians, Developers
| ☐ | Business Unit and Site Leads
☐
☐
☐
II - Prepare
|  | 4.0 Strategize |  |  |  |  | 5.0 Govern |  |  |  |  | 6.0 Align |  | Need to change order - put strategize last after the governance and alignment activities.
|  | ☐ | Determine Approach Based on Analysis: |  |  |  | ☐ | Identify and Review Applicable security policies and procedures. |  |  |  | ☐ | Identify other system and business related activity present at this time. Describe how it impacts vulnerability remediation efforts including upgrades, maintenance, and replacements
|  | ☐ | Patch - install additional libraries, software, and firmware necessary to address vulnerability |  |  |  | ☐ | Determine Risk Exception process if needed. |  |  |  | ☐ | Identify changes in business processes or value streams that may occur simultaneously with remediation activities
|  | ☐ | Upgrade - Install major release or version number that addresses vulnerability and provides additional system features desired. |  |  |  | ☐ | Determine executive approvals needed based on strategy. |  |  |  | ☐ | Identify the implementation of other security controls, policies, or configurations that may occur simultaneously with vulnerability remediation activities. (ie segmentation, FW policy changes, threat protection etc.
|  | ☐ | Mitigate with other security controls- monitor, remove, or configure other system features. Install or leverage infrastructure tools like firewalls or segmentation that would lower the risk of the vulnerability without installing new software on the system. |  |  |  | ☐ | Record risk within applicable risk register |  |  |  | ☐ | Identify any architectural changes relevant to vulnerability remediation.
|  | ☐ | Accept Risk without direct mitigation - request exception (Most likely requires executive approval and contingency plans |  |  |  | ☐ | Determine Configuration Control Board (CCB) approvals for system changes. |  |  |  | ☐
|  | ☐ | Define technical, business, and system requirements based on strategy. |  |  |  | ☐ | Identify and determine contractual obligations or restraints for patching and remediation activities. |  |  |  | ☐
|  | ☐ |  |  |  |  | ☐ |  |  |  |  | ☐
| Activity | [5 empty] | Description |  |  | Output
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| Activity | [5 empty] | Description |  |  | Output
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| Activity | [5 empty] | Description |  |  | Output
☐
☐
☐
☐
☐
7.0 Plan Use this section to plan details needed to execute the vulnerability remediation or mitigation efforts.
CATEGORY
|  | Resources |  |  |  | Responsibilities |  |  |  | Description and Notes
| ☐ | Network Administration and Engineering |  |  |  | Plan, execute, and monitor network changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | Security Administration and Engineering |  |  |  | Plan, execute, and monitor security changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | System Administration |  |  |  | Plan, execute, and monitor system changes and activity during remediation. Provide support if errors or issues occur during remediation.
| ☐ | Site Operations Leads |  |  |  | Direct business failover operations and perform testing and verificaion of return to normal business operations.
| ☐ | Site Technical Support |  |  |  | Hands on support for any site specific network or systems issues.
| ☐ | 3rd Party IT support |  |  |  | Provide Tier 1-3 network and systems support should an incident arise during patching activities. |  |  |  | Include any individuals assigned to your organization to support the system in question.
| ☐ | Vendors |  |  |  | Consultation and support during patch activities.
☐
☐
☐
☐
☐
☐
| ☐ | Schedule Type |  |  |  | Potential Dates | Dependencies |  |  | Description and Notes
| ☐ | Testing
| ☐ | Approvals
| ☐ | Change Management
| ☐ | Implementation Management
| ☐ | Configuration Control Board
| ☐ | Access Control - FW rule modifications
| ☐ | Execution Dates
☐
☐
| ☐ | Documentation
| ☐ | Vendor Upgrade and Patching procedures
| ☐ | Configuration Management Plans
| ☐ | Change Management policies and procedures | [7 empty] | Used to identify the process controlling changes within the system and organization.
| ☐ | System configuration and support playbooks
| ☐ | Incident Management Plans
| ☐ | Business Continuity Plans | [7 empty] | Used to identify how sites will failover key business processes if necessary during remediation activities. Also used to identify decision makers to activate continuity plans if an incident occures.
| ☐ | Disaster Recovery Plans | [7 empty] | Used to identify recovery, backup, and alternate site procedures.
| ☐ | Security policies and procedures
☐
☐
☐
☐
☐
| ☐ | Testing
| ☐ | Identify testing resources and systems.
| ☐ | Identify changes to testing environment necessary to evaluate patching procedures.
| ☐ | Identify additional tools and applications used to test patch or remediation activities.
☐
☐
☐
☐
☐
☐
| ☐ | Business Continuity
| ☐ | Identify business and process failovers during upgrades or patching.
| ☐ | Identify alternate sites for business activities during patching and failovers.
☐
☐
☐
| ☐ | Disaster Recovery
| ☐ | Identify backup systems, alternate sites, or regions used for disaster recover.
| ☐ | Identify data and configuration backups required for recovery if necessary.
| ☐ | Identify system failover procedures for use during patching and upgrades.
| ☐ | Identify rollback procedures for both systems and data.
☐
☐
☐
☐
☐
| ☐ | Configuration Management
| ☐ | Review and determine method of naming and controlling configuration items for the upgrade. | [7 empty] | If this is a vendor controlled/operated system or service, they most likely will have this information. If not, this will require greenfield planning.
| ☐ | Determine changes that do not require configuration control or change management control.
| ☐ | Identify impacted configuration items (CI)
| ☐ | Identify configurations that may impact the security of the system | [7 empty] | This includes changes in access, authentication, encryption, or any security capability included in the system.
| ☐ | Identify system component inventory
| ☐ | Identify impacted configuration items (CI) | [7 empty] | Servers, workstations, HDMI, OS, firmware, communications devices, or application suite tracked.
| ☐ | Identify a baseline configuration for the system | [7 empty] | Set of specifications that has been reviewed and agreed upon for operating the system.
| ☐ | Identify Configuration monitoring processes required during change
| ☐ | Perform a security impact analysis to determine whether upgrade, patch, or reconfiguration changes security functionality or existing controls | [7 empty] | This prevents accidental errors that could impact the surity of a system - ie access, authorizations, encryption, privacy, etc.
| ☐ | Make Change Requests for changes of impacted CIs.
| ☐ | Security Management
| ☐ | Identify changes to access control/FW devices necessary
| ☐ | Review amd determine whether additional authorizations and privileges are necessary for staff to execute changes.
| ☐ | Apply for additional privileged access if necessary prior to the upgrade.
| ☐ | Review whether remote access is necessary for 3rd parties to participate in patch and upgrade activities.
| ☐ | Apply for additional remote access if necessary prior to the upgrade.
☐
☐
☐
☐
| ☐ | Network Management
| ☐ | Identify network (vlan, IP addressing, routing, and switching changes that may be necessary for remediation or mitigation of the risk or vulnerability.
| ☐ | Identify network capacity or performance issues that may impact an upgrade or patch activities.
| ☐ | Identify other network related activity that may impact vulnerability remediation plans.
☐
| ☐ | Incident Management
| ☐ | Identify procedures to request support during an incident
| ☐ | Identify indivduals who fill the incidenet manager role if necessary.
| ☐ | Identify groups or individuals that may serve as the incident resolution team if necessary.
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
| ☐ | Closure
☐
☐
☐
☐
☐
☐
☐
☐
☐
III - Execute
IV - Evolve

## Parking Lot
https://mckessoncorp.sharepoint.com/sites/Policies/SitePages/Threat-and-Vulnerability-Management-Policy.aspx?OR=Teams-HL&CT=1651070004382&params=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yMjA0MDExMTQwOSJ9

## Ideas
Would like to provide hyperlinks in each one of these activities to where this should be done or another tracking tool within this spreadsheet or smart sheet.
Note: do I need to provide a checklist for OT team?
We need a configuration control board (CCB)
https://www.first.org/cvss/calculator/3.0#CVSS:3.0/AV:N/AC:L/PR:N/UI:N/S:U/C:H/I:H/A:H

## Risk Scale
CVE Severity | CVSS v2 | CVSS v3
Low | 0.0-3.9 | 0.1-3.9
Med | 4.0-6.9 | 4.0-6.9
High | 7.0-10.0 | 7.0-8.9
Critical |  | 9.0-10.0
Eyeball Risk
Segmentation Level in Place | CVSS v3 High Severity | CVSS v3 Medium Severity | CVSS v2 Low | CVSS v3 Low Severity
S4-5* | Low | Low | Low | Low
S3 | Medium | Low |  | Low
S2 | Medium-High | Medium |  | Low
S1 | Medium-High | Medium |  | Low
S0 | High | Medium-High |  | Medium
None | High | Medium-High |  | Medium
Eyeball Risk with Impact | Low Impact | Medium Impact |  | High Impact
Low | Low | Medium |  | Medium
Medium | Low | Medium |  | Medium-High
Medium-High | Medium | Medium-High |  | High
High | Medium-High | High |  | High
Assumptions:
1. Threat Model is constant across all DCs, with little to no variation.
2. Threat protection is enabled as soon as the OT FW is installed and connected to the network. - IPS/IDS (S1)
3. Armis risk is inconsistently measured across all device and not taken into factor in the risk model
4. Threats are monitored consistently across all DCs by iSOC (detective controls)
5. IT devices that support OT utilize a standard security toolset approved by McKesson.
6. Each DC has a different impact based on the revenue, products distributed, and level of operations.